## Sheet1
|  | March |  |  | April |  |  |  |  | May |  |  |  | June
|  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Overall | Related contents acquisition | April 7: Midterm Demo; April 8: Midterm Exam; June 14: Final Demo
Implement Android GUI | bar: March 3 to April 6; April 9 to May 13
Implement psychological analysis function | bar: March 3 to April 6; April 9 to May 11
Implement writing psychological state function | bar: March 3 to March 4
Implement speech recognition function | bar: April 9 to May 10
Implement translation function | bar: May 11 to May 12
Implement log-in function & DB linking | bar: April 5 to April 6
Implement blood glucose level function & DB linking | bar: April 6; April 9
Implement medication administration function & DB linking | bar: April 9 to May 10
Implement diet management function & DB linking | bar: May 10 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13
Testing | bar: April 6; May 13
Kim, Myeong Gyu UI | Diary UI | April 7: Midterm Demo; April 8: Midterm Exam; June 14: Final Demo
Login, Sign-in UI | bar: April 5 to April 6
Blood glucose level UI | bar: April 6; April 9
Medication administration tracking UI | bar: April 9 to May 10
Diet management UI | bar: May 10 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13
Sung, Ho Joon App. | Diary Functions | April 7: Midterm Demo; April 8: Midterm Exam; June 14: Final Demo
Login, Sign-in Functions | bar: April 5 to April 6
Sentiment analysis function | bar: March 3 to April 6; April 9 to May 11
Blood glucose level function | bar: April 6; April 9
Medication administration tracking function | bar: April 9 to May 10
Diet management function | bar: May 10 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13
Nam, Geun Woo Server | Database design | April 7: Midterm Demo; April 8: Midterm Exam; June 14: Final Demo
Server-side scripting | bar: March 4 to April 6; April 9 to May 10
Sentiment analysis function | bar: March 3 to April 6; April 9 to May 11
Implement encryption function | bar: May 12 to May 13
Implement additional function | bar: May 12 to May 13